# Meeting Minutes — Project Explanation and Adding Images

Date: 21 April 2026
Present: Daniel Sikar, Pritish Ranjan PG-Verma, Josh, Andrew
Topic: Project walkthrough for newer team members; embedding methodology; image and video extension; HPC coordination

## 1. Project Walkthrough and Core Hypothesis

- Daniel gave a from-scratch explanation of transformer architecture, tokenisation, embeddings, and the motivation for the project.

- The working hypothesis remains that embeddings retain contextual information from the input, even when the model behaves as a black box at output level.

- Current validation work is based on text embeddings from emotion-labelled sentences. Each sentence is passed through a pre-trained model, an embedding is extracted, and the resulting points are analysed geometrically.

- The team clarified that the current phase does not train the base model for these initial experiments; it uses pre-trained models to generate embeddings and studies the resulting geometry.

- A key methodological point raised in discussion was that the paper must explicitly state which layer / extraction point the embedding comes from in each model architecture.

Action — Daniel / Pritish: Make sure the methods section records the exact embedding extraction point for each model used.

## 2. Text Embedding Results Recap

- The active text work remains focused on emotion-labelled sentence datasets, especially the six-emotion multiclass setting.

- Each sentence corresponds to one point in embedding space; centroids and density-style analyses are computed in the full embedding dimension, with PCA used only for visualisation.

- The team revisited the interpretation of the radial plots:

  - the previous “density” wording was misleading for one plot;

  - that plot is better described as number of data points per radial-distance band;

  - absolute density, when normalised by available volume, behaves as originally expected near the centroid.

- Discussion reaffirmed the conceptual result that there appears to be no “pure emotion” point at the centre; instead, points occupy regions at non-zero distance from the centroid.

Action — Pritish: Update plot wording where needed so radial-band counts are not labelled as density.

## 3. Image Extension

- The next major extension is from text into images, using the same general idea: generate embeddings, plot them, and test whether contextual properties can be recovered geometrically.

- One line of discussion focused on whether image embeddings could reveal multiple independent contextual attributes at once, for example:

  - object category, such as car / bus / truck;

  - colour, such as black / non-black.

- The proposed logic is to reuse the same embeddings and test different labelings against them, rather than generating a separate representation for each concept.

- This would allow the team to test whether the same image embedding space simultaneously supports clustering by more than one valid contextual attribute.

- Daniel showed the current experiment repository structure and explained the expected folder layout for image work, including dedicated folders for experiments, reports, source code, and datasets.

Action — Team: Implement image experiments inside the shared repository structure under the dedicated images area.

## 4. Video Extension

- The group also discussed how video could be handled as the next extension after images.

- The working idea is to segment a video over time and generate embeddings for each segment rather than treating the whole video as a single unit.

- A frame-by-frame approach may be too granular, so a coarser segmentation such as fixed timestamps or short intervals was suggested as a more practical starting point.

- The implementation sessions for video will be vibe coded as a group with Andrew, Daniel, Josh, and Pritish working together.

Action — Andrew / Daniel / Josh / Pritish: Organise group vibe-coding sessions to implement the first video pipeline.

## 5. HPC Access and Coordination

- The team confirmed that all four members either now have HPC access or are in the process of getting fully set up.

- Daniel noted that, with four accounts available, the group should be able to run multiple experiments in parallel and make fuller use of available GPU resources.

- Setup remains a practical barrier for some members, particularly in preparing projects correctly for HPC execution rather than just obtaining account access.

- Daniel offered to share the commands needed to get others running more quickly.

Action — Daniel: Share / resend the essential HPC setup commands to the team.

Action — Josh / Andrew: Complete HPC setup and confirm they can run project code there.

## 6. Current Qwen Run and Repository Follow-Up

- During the meeting, a Qwen-based run on the HPC completed and pushed JSON outputs.

- The initial push did not include the required .npy embedding files because they had been excluded.

- The team identified that the embeddings are still needed for downstream plotting and analysis, so the run output handling needs to be corrected.

- Once the embedding files are available in the repository, the existing analysis pipeline can be run to generate the corresponding plots.

Action — Daniel: Force the required .npy embedding files into the repository output for the Qwen run.

Action — Pritish: Run the analysis pipeline on the completed outputs once the embedding files are available.

## General Notes

- This meeting mainly served to bring newer members up to speed on the conceptual basis of the project before moving fully into image and video experiments.

- The repository structure and workflow are now clear enough that image tasks can be split across the group while keeping outputs in a consistent layout.

- Coursework discussion at the end of the transcript was intentionally excluded from these minutes.